## Slide 1
ICEG
Open Standards
March 24th, 2021
(Raf Buyle, Marc Bruyland)

## Slide 2: Agenda
Recap
Proposed thematic working groups
Proposal

## Slide 3: Opportunity
The Single Digital Gateway (SDG) obliges the EU member states to agree on semantic issues regarding 21 cross-border procedures.
Inside BE, this will require collaboration between <> levels of the government.
The data standardization group under ICEG provides the right organizational format to do so.

## Slide 4: Hurdle
Launching a thematic workgroup requires resources to hire (estimated budget xxx K per initiative).
The funding has to come from different government parties (federal + regional).
In 2020 there was no smooth process to do so.

## Slide 5: Proposal (ICEG 2020-12-02)
We asked a funding of xxx K for 2021.
xxx K FOD BOSA
xxx K Flanders
xxx K French community
xxx K Walloon region
This would allow us to execute 3 thematic workgroups.
Agreement in principle was given by the ICEG committee.

## Slide 6: Proposal: actuals
Actuals xxx K – xxx K
xxx K FOD BOSA: GO
xxx K Flanders: GO
xxx K French speaking community: maybe by end of 2021
xxx K Walloon region: agreement in principle (GO/NOGO in June 2021 – unclear how the budget can be used)
This allows us to execute 2 thematic workgroups.
The first in Q2 2021
The second in Q3 2021 (condition: Walloon GO)

## Slide 7: Agenda
Recap
Proposed thematic working groups
Proposal

## Slide 8: Proposed topics 2021
Proposed topics by the working group:
thematic workgroup on public services and public organisations (SDG).
thematic workgroup on buildings
Project charters:
thematic/org-services at master · belgif/thematic (github.com)
thematic/buildings at master · belgif/thematic (github.com)

## Slide 9: ICEG Public Services and Public Organisations
Via this initiative, the various stakeholders wish to semantically model the different data flows and standardize the structure of the data for the subject public organisation and public services.
This initiative is relevant in the context of SDG.

## Slide 10: ICEG Public Services and Public Organisations
Start: indicative TBD
Duration: 7 months
Thematic Workshop
Thematic Workshop
Thematic Workshop
Start Public review
End Public review
2021
Business Workshop
April
May
June
July
August
September
October
November
December
Thematic Workshop

## Slide 11: ICEG Public Services and Public Organisations
Budget: 43 days
Defining a semantic data standard |  | 
Task | Profile | MD
Drawing up an overview of information needs based on analysis of available documentation and existing standards | Semantic expert | 5
Organizing a business workshop with stakeholders to validate and further expand the information needs | Semantic expert | 4
Organizing and facilitating 4 workshops composed of domain experts and processing their feedback. | Semantic expert | 20
Preparation of reusable documentation for the information model and publication on data.vlaanderen.be: RDF vocabulary HTML documentation for the vocabulary with terms and definitions UML diagram HTML documentation for the UML diagram SHACL validation rules JSON-LD context file | Semantic expert | 4
Integration in the ICEG system of vocabularies | Technical expert | 3
Integration in the OSLO system of vocabularies | Technical expert | 2
Support in terms of process and method and validation by the Steering Committee | Project manager | 2
Project management | Project manager | 3
 | Total | 43

## Slide 12: ICEG Building
Via this initiative, the various stakeholders wish to semantically model the different data flows and standardize the structure of the data for the subject building. The focus is on terms related to buildings and building units.
The objective is to make the data accessible as Linked Open Data and to define standard interfaces (APIs) in order to simplify collaboration and integration of the various services and tools. The objective is to make the data easily reusable for all stakeholders.

## Slide 13: ICEG Building
Start: indicative TBD
Duration: 7 months
Business Workshop
Thematic Workshop
Thematic Workshop
Thematic Workshop
Start Public review
End Public review
Implementation of draft specifications
2021
January
February
March
April
August
October
November
December
September
2022

## Slide 14: ICEG Building
Defining a semantic data standard |  | 
Task | Profile | MD
Drawing up an overview of information needs based on analysis of available documentation and existing standards | Semantic expert | 4
Organizing a business workshop with stakeholders to validate and further expand the information needs | Semantic expert | 4
Organizing and facilitating 3 workshops composed of domain experts and processing their feedback. | Semantic expert | 15
Preparation of reusable documentation for the information model and publication on data.vlaanderen.be: RDF vocabulary HTML documentation for the vocabulary with terms and definitions UML diagram HTML documentation for the UML diagram SHACL validation rules JSON-LD context file | Semantic expert | 4
Integration in the ICEG system of vocabularies | Technical expert | 3
Integration in the OSLO system of vocabularies | Technical expert | 2
Support in terms of process and method and validation by the Steering Committee | Project manager | 2
Project management | Project manager | 3
 | Total | 37
Budget: 37 days

## Slide 15: Agenda
Recap
Proposed thematic working groups
Proposal

## Slide 16: Decision ICEG
Proposed topics by the working group:
(A) thematic workgroup on public services and public organisations (SDG).
(B) thematic workgroup on buildings
Proposed order to execute the working groups:
(A) startdate 2021-04
(B) startdate 2021-09 – condition: Walloon budget